## Regional Exchange Timeline
Phase | In-Person or Virtual? | Activity | Responsible Party | When | Deadline (Feb 8, 2018) | Reference | Status
Pre-planning | In-person, Virtual | Determine broad TPM issue(s) to be addressed |  | Up to six months prior to event | 2018-03-15 | https://www.tpm-portal.com/ret/#pre-planning
Pre-planning | In-person, Virtual | Determine expected outcomes, what is in and out of scope |  | Up to six months prior to event | 2018-04-01 | https://www.tpm-portal.com/ret/#pre-planning
Pre-planning | In-person, Virtual | Select date, time, location and host, whether the session will be in-person or virtual |  | Up to six months prior to event | 2018-04-15 | https://www.tpm-portal.com/ret/#pre-planning
Pre-planning | In-person, Virtual | Select candidate agencies and participants |  | Up to six months prior to event | 2018-05-01 | https://www.tpm-portal.com/ret/#pre-planning
Pre-planning | In-person, Virtual | Determine lead, support and resources needed for event |  | Up to six months prior to event |  | https://www.tpm-portal.com/ret/#pre-planning
Pre-planning | In-person, Virtual | Determine assumptions, risks and constraints |  | Up to six months prior to event |  | https://www.tpm-portal.com/ret/#pre-planning
Pre-planning | In-person, Virtual | Draft high-level, strawman framework for kickoff meeting |  | Up to six months prior to event | 2018-05-30 | https://www.tpm-portal.com/ret/#pre-planning
Pre-planning | In-person, Virtual | Conduct attendee survey to refine and finalize topics, if needed |  | Up to six months prior to event | 2018-08-07 | https://www.tpm-portal.com/ret/#pre-planning
Pre-planning | In-person, Virtual | Compile survey results and share with planning team |  | Up to six months prior to event | 2018-09-01 | https://www.tpm-portal.com/ret/#pre-planning
Planning and Implementation | In-person, Virtual | Schedule planning team kickoff to review and refine scope and objectives; set up additional planning meetings, as needed |  | Four months prior to event | 2018-06-30 | https://www.tpm-portal.com/ret/#planning-and-implementation
Planning and Implementation | In-person, Virtual | Review and finalize draft scoping document with planning team |  | Four months prior to event |  | https://www.tpm-portal.com/ret/#planning-and-implementation
Planning and Implementation | In-person, Virtual | Invite participants (include expectations) |  | Four months prior to event |  | https://www.tpm-portal.com/ret/#planning-and-implementation
Planning and Implementation | In-person, Virtual | Start to plan logistics (if in-person, includes site details, hotel, meals, reimbursement) |  | Three months prior to event |  | https://www.tpm-portal.com/ret/#planning-and-implementation
Planning and Implementation | In-person, Virtual | Coordinate presentations |  | Two months prior to event | 2018-02-01 | https://www.tpm-portal.com/ret/#planning-and-implementation
Planning and Implementation | In-person, Virtual | Develop materials |  | Two months prior to event |  | https://www.tpm-portal.com/ret/#planning-and-implementation
Planning and Implementation | In-person, Virtual | Finalize logistics |  | Two months prior to event |  | https://www.tpm-portal.com/ret/#planning-and-implementation
Planning and Implementation | In-person, Virtual | Finalize materials |  | One month prior to event |  | https://www.tpm-portal.com/ret/#planning-and-implementation
Planning and Implementation | In-person, Virtual | Send pre-event packet |  | Two weeks prior to event |  | https://www.tpm-portal.com/ret/#planning-and-implementation
Planning and Implementation | Virtual | Conduct prep session with planning team and moderators to ensure everyone is comfortable with and able to use the technology |  | One week prior to event |  | https://www.tpm-portal.com/ret/#planning-and-implementation
Planning and Implementation | In-person | Print agendas, signs and other documents (in-person event) |  | By event date |  | https://www.tpm-portal.com/ret/#planning-and-implementation
Planning and Implementation | Virtual | Email final agenda and other documents, if needed (virtual event) |  | By event date |  | https://www.tpm-portal.com/ret/#planning-and-implementation
Planning and Implementation | In-person | Create name tags or name tents (in-person event) |  | By event date | 2018-02-06 | https://www.tpm-portal.com/ret/#planning-and-implementation
Planning and Implementation | In-person | Develop sign-in sheets for attendees (in-person event) |  | By event date | 2018-02-07 | https://www.tpm-portal.com/ret/#planning-and-implementation
Planning and Implementation | In-person | Final room logistics (in-person event) - Ensure room is set up; confirm sound, video and microphones; ensure presentation displays properly |  | Event date |  | https://www.tpm-portal.com/ret/#planning-and-implementation
Planning and Implementation | Virtual | Final webinar logistics (virtual event) - Sign-in at least 30 minutes in advance of event to ensure technology is working and presentation displays properly |  | Event date |  | https://www.tpm-portal.com/ret/#planning-and-implementation
Planning and Implementation | In-person, Virtual | Conduct regional exchange |  | Event date |  | https://www.tpm-portal.com/ret/#planning-and-implementation
Planning and Implementation | In-person, Virtual | Email thanks to planning committee and aupport staff |  | Day after event |  | https://www.tpm-portal.com/ret/#planning-and-implementation
Post-event | In-person, Virtual | Post-event email with feedback form (or electronic survey), link to presentations and handouts to all attendees |  | Day after event | 2018-02-09 | https://www.tpm-portal.com/ret/#post-event
Post-event | In-person, Virtual | Conduct post-event debrief with planning committee, sponsor |  | Day after event to one week after event |  | https://www.tpm-portal.com/ret/#post-event
Post-event | In-person, Virtual | Document proceedings and summarize results (if event is virtual, use recording function on web conferencing software to capture the event proceedings and facilitate drafting notes) |  | One week after event |  | https://www.tpm-portal.com/ret/#post-event
Post-event | In-person, Virtual | Draft and finalize Summary Report |  | One month after event |  | https://www.tpm-portal.com/ret/#post-event
Post-event | In-person, Virtual | Publish Summary Report to TPM Portal (via TPM Pooled Fund support team) | TPM Pooled Fund Support Team | One month after event |  | Email to: lrichter@spypondpartners.com
Post-event | In-person, Virtual | Share link to published Summary Report with attendees, along with reminder to complete feedback form (or electronic survey) | TPM Pooled Fund Support Team | One month after event |  | Email to: lrichter@spypondpartners.com
Post-event | In-person, Virtual | Conduct post-event action planning |  | One to two months after event |  | Email to: lrichter@spypondpartners.com
Post-event | In-person, Virtual | Draft TPM Newsletter article about event; send to TPM Pooled Fund support team |  | Calendar quarter after event | 2018-02-12 | Email to: lrichter@spypondpartners.com
Post-event | In-person, Virtual | Compile event survey results and share with TPM Pooled Fund support team |  | Calendar quarter after event | 2018-02-23 | Email to: lrichter@spypondpartners.com
Post-event | In-person, Virtual | Share planning lessons learned with TPM Pooled Fund support team |  | Calendar quarter after event | 2018-02-28 | Email to: lrichter@spypondpartners.com